## Dashboard
CoopBank Website Redesign
SG-2026-0101 ¦ Cooperative Bank Tanzania Plc.
Total Tasks | Completed | In Progress | Blocked/Awaiting | Completion %
Milestone Progress
Milestone | Total | Done | In Progress | Blocked | Progress | Status
PM & Admin
Discovery & Planning
Design & Build
Client Review & Revisions
Content & Localization
Testing & QA
Go-Live & Handover
Items Blocked on Client
Task | Tags | Status | Blocker Description

## Tasks
SG-2026-0101 — CoopBank Task Tracker
Use Status dropdown to update. Changes auto-color. Tags are comma-separated. Subtasks link to Subtasks tab.
ID | Task Name | Milestone | Owner | Status | Tags | Priority | Start Date | Due Date | Subtasks | Dependencies / Notes
77 | Weekly Client Status Update (CoopBank) | PM & Admin | Neema | Awaiting Feedback | Recurring | High | 2026-03-18 | 2026-04-25 |  | Weekly cadence
78 | Invoice Preparation & Payment Follow-up | PM & Admin | Neema | Not Started | Finance | High | 2026-03-20 | 2026-04-25 |  | 40% commencement due
79 | Project Timeline & Risk Management | PM & Admin | Neema | Awaiting Feedback | PM | High | 2026-03-18 | 2026-04-25
80 | Client Communication & Meeting Coordination | PM & Admin | Neema | Awaiting Feedback | PM | High | 2026-03-18 | 2026-04-25
81 | Contract & Scope Documentation | PM & Admin | Neema | Awaiting Feedback | Legal | High | 2026-03-20 | 2026-03-22
48 | Discovery & Stakeholder Requirements | Discovery & Planning | Jumbe + Neema | Complete | Research | Medium | 2026-03-06 | 2026-03-08
49 | Competitor Analysis (NMB, CRDB, NBC, Stanbic) | Discovery & Planning | Jumbe + Neema | Complete | Research | Medium | 2026-03-07 | 2026-03-09
50 | Sitemap & Information Architecture | Discovery & Planning | Jumbe + Neema | Complete | UX | Medium | 2026-03-08 | 2026-03-10
51 | Brand Asset Collection | Discovery & Planning | Neema | Complete | Design | Medium | 2026-03-08 | 2026-03-11
52 | Content Audit & Copywriting | Discovery & Planning | Jumbe + Neema | Complete | Content | Medium | 2026-03-09 | 2026-03-14
53 | Next.js Project Setup & Architecture | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-12 | 2026-03-13
54 | Homepage Build (Hero, Forex, Products, Stats) | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-13 | 2026-03-15
55 | Personal Banking & Loan Products Pages | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-15 | 2026-03-16
56 | Digital Banking Pages (CoopNet, Wakala, USSD, QR) | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-16 | 2026-03-17
57 | About Us, Board & Management Pages | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-17 | 2026-03-18
58 | Tenders, Whistleblower, Careers Pages | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-17 | 2026-03-17
59 | Navbar, Footer & Shared Components | Design & Build | Jumbe | Complete | Dev | Medium | 2026-03-14 | 2026-03-18
60 | Mshirika AI Chatbot Integration | Design & Build | Jumbe | Complete | AI | Medium | 2026-03-18 | 2026-03-18
61 | GA4 Analytics & Staging Deployment | Design & Build | Jumbe | Complete | DevOps | Medium | 2026-03-17 | 2026-03-18
62 | Submit First Draft to CoopBank Marketing | Client Review & Revisions | Jumbe + Neema | Complete | Milestone | Medium | 2026-03-18 | 2026-03-18 |  | Sent to Oscar Rubasha
63 | Collect Client Feedback (Round 1) | Client Review & Revisions | Neema | Complete | Client | High | 2026-03-18 | 2026-03-25 |  | Received 2026-03-26
64 | Implement Design Revisions (Round 1) | Client Review & Revisions | Jumbe | Complete | Dev | Medium | 2026-03-25 | 2026-03-29 |  | Colors, forex, products, cards, content
65 | Collect Client Feedback (Round 2) | Client Review & Revisions | Neema | Not Started | Client | Medium | 2026-03-29 | 2026-04-01 |  | After pending builds complete
109 | Implement Design Revisions (Round 2) | Client Review & Revisions |  | Not Started | Dev | Medium |  |  |  | Depends on: Round 2 feedback
110 | Collect Client Feedback (Round 3 - Final) | Client Review & Revisions |  | Not Started | Client | Medium |  |  |  | Final review before QA
111 | Implement Final Revisions (Round 3) | Client Review & Revisions |  | Not Started | Dev | Medium |  |  |  | Last changes before testing
82 | Build: Business Banking Page | Client Review & Revisions | Jumbe | Not Started | Build | Medium | 2026-03-27 | 2026-03-29 | 0/10
83 | Build: Contact Us Page | Client Review & Revisions | Jumbe | Not Started | Build | Medium | 2026-03-27 | 2026-03-28 | 0/10 | Needs: email domain (#113)
84 | Build: FAQs Page | Client Review & Revisions | Jumbe | Not Started | Build | Medium | 2026-03-28 | 2026-03-29 | 0/13
85 | Build: Blog / News & Updates Page | Client Review & Revisions | Jumbe | Not Started | Build | Medium | 2026-03-29 | 2026-03-31 | 0/10
86 | Build: Privacy Policy & Terms Pages | Client Review & Revisions | Neema | Not Started | Build, Legal | Medium | 2026-03-29 | 2026-03-30 | 0/8 | Needs: approved legal content
87 | Build: Cookie Consent Banner | Client Review & Revisions | Jumbe | Not Started | Build | Medium | 2026-03-30 | 2026-03-30 | 0/9
89 | Figma Design System: Complete & Deliver | Client Review & Revisions | Jumbe | Not Started | Design | Low | 2026-03-29 | 2026-04-03 |  | Deliverable to client
90 | Figma: Component Library & Style Guide | Client Review & Revisions | Jumbe | Not Started | Design | Medium | 2026-04-01 | 2026-04-03
112 | Awaiting: Official Product Master List | Client Review & Revisions | Oscar (CBT) | Awaiting Client | Blocker, Products | Critical |  |  | 0/7 | Msomi vs Wanafunzi, Mafao etc.
113 | Awaiting: Email Domain Confirmation | Client Review & Revisions | CBT IT | Awaiting Client | Blocker, Config | Critical |  |  | 0/8 | @coopbank vs @cbtbank
114 | Awaiting: Brand Guide / Visual Reference | Client Review & Revisions | CBT Marketing | Awaiting Client | Blocker, Design | High |  |  | 0/9 | Dashed white unclear
115 | Awaiting: About Us Content (Bank-Approved) | Client Review & Revisions | Oscar (CBT) | Awaiting Client | Blocker, Content | Critical |  |  | 0/11 | Mission, Vision, Values, Story
116 | Awaiting: Account Opening CTAs | Client Review & Revisions | CBT Ops | Awaiting Client | Blocker, UX | Critical |  |  | 0/12 | Where do buttons link?
117 | Awaiting: Agent Application Form | Client Review & Revisions | CBT Ops | Awaiting Client | Blocker, UX | High |  |  | 0/7 | Destination unknown
66 | Swahili Translation - All Pages | Content & Localization | Neema | Not Started | i18n | Medium | 2026-04-01 | 2026-04-07 | 0/15
67 | Branch Directory with Google Maps | Content & Localization | Jumbe | Not Started | Build, Maps | Medium | 2026-04-03 | 2026-04-06 | 0/10 | Needs: branch data from CBT
68 | Final Content Population & Media | Content & Localization | Neema | Not Started | Content | Medium | 2026-04-05 | 2026-04-08 | 0/10
69 | Blog/News Section Setup | Content & Localization | Jumbe | Not Started | Build | Medium | 2026-04-07 | 2026-04-09
88 | Branch Locator: Google Maps Integration | Content & Localization | Jumbe | Not Started | Build, Maps | Medium | 2026-04-03 | 2026-04-06 |  | Depends: #67 + branch data
91 | API Discovery: Map CoopBank Endpoints | Content & Localization | Jumbe | Not Started | API | High | 2026-04-01 | 2026-04-05 |  | Unblocks all API work
92 | API Integration: Forex Rates | Content & Localization | Jumbe | Not Started | API | Medium | 2026-04-05 | 2026-04-07 |  | Depends: #91 + #120
93 | API Integration: Loan Calculator | Content & Localization | Jumbe | Not Started | API | Medium | 2026-04-05 | 2026-04-07 |  | Depends: #91
94 | API Integration: Careers & Tenders | Content & Localization | Jumbe | Not Started | API | Medium | 2026-04-07 | 2026-04-09 |  | Depends: #91
95 | API Integration: Branch Data | Content & Localization | Jumbe | Not Started | API | Medium | 2026-04-06 | 2026-04-08 |  | Depends: #91 + #118
118 | Awaiting: Agent Database for Wakala | Content & Localization | CBT Ops | Awaiting Client | Blocker, Data | Critical |  |  | 0/13 | Name ¦ Location ¦ Contact
119 | Awaiting: POS Services List | Content & Localization | CBT Digital | Awaiting Client | Blocker, Content | Critical |  |  | 0/9 | Wakala POS services
120 | Awaiting: Forex Rate Data Source | Content & Localization | CBT Treasury | Awaiting Client | Blocker, API | High |  |  | 0/11 | API or manual?
121 | Awaiting: Cards & Payments Specs | Content & Localization | CBT Marketing | Awaiting Client | Blocker, Content | High |  |  | 0/10 | Visa Prepaid specs
122 | Awaiting: Treasury/FX Page Decision | Content & Localization | CBT Mgmt | Awaiting Client | Blocker, Scope | Medium |  |  | 0/7 | Separate page needed?
123 | Awaiting: Investors/Corp Governance | Content & Localization | CBT Mgmt | Awaiting Client | Blocker, Scope | Medium |  |  | 0/11 | Ready for launch?
70 | Cross-Browser & Mobile Testing | Testing & QA | Jumbe + Neema | Not Started | QA | Medium | 2026-04-10 | 2026-04-12 | 0/12
71 | SEO & Performance Optimization | Testing & QA | Jumbe | Not Started | SEO | Medium | 2026-04-10 | 2026-04-13 | 0/12 | Lighthouse 90+
72 | Security Hardening & BOT Compliance | Testing & QA | Jumbe | Not Started | Security | High | 2026-04-13 | 2026-04-15 | 0/10 | OWASP + Bank of Tanzania
73 | UAT with CoopBank IT & Marketing | Testing & QA | Jumbe + Neema | Not Started | UAT, Client | High | 2026-04-15 | 2026-04-17 | 0/10 | Needs sign-off
74 | DNS Migration & Production Go-Live | Go-Live & Handover | Jumbe | Not Started | DevOps | Critical | 2026-04-17 | 2026-04-19 | 0/11 | Needs DNS access
75 | Staff Training Session | Go-Live & Handover | Jumbe + Neema | Not Started | Training | Medium | 2026-04-19 | 2026-04-21 | 0/10
76 | Post-Launch Monitoring (30 Days) | Go-Live & Handover | Jumbe | Not Started | Support | Medium | 2026-04-21 | 2026-05-19 | 0/11

## Subtasks
Subtask Details — Check Done when complete
Task ID | Task Name | Subtask | Done | Assigned To | Notes
82 | Build: Business Banking Page | Design hero section with glassmorphism panel
82 |  | Build Business Current Account section (TZS, USD, EUR, GBP)
82 |  | Build Business Savings Account section
82 |  | Build Trade Finance section (LCs, guarantees, bills)
82 |  | Build Cash Management section
82 |  | Build Payroll Services section
82 |  | Build Business Loans overview with CTA
82 |  | Add product comparison table
82 |  | Add Open Business Account CTA (pending destination)
82 |  | Mobile responsive layout and testing
83 | Build: Contact Us Page | Build hero with contact information cards
83 |  | Add phone: +255 27 275 4470
83 |  | Add email (pending domain confirmation)
83 |  | Build contact form (name, email, phone, subject, message)
83 |  | Add form validation and submission handler
83 |  | Embed Google Maps with HQ pin
83 |  | Add operating hours section
83 |  | Add social media links
83 |  | Add quick links to Branch/Agent Locator
83 |  | Mobile responsive layout
84 | Build: FAQs Page | Design FAQ layout with category tabs
84 |  | Create categories: General, Accounts, Digital, Loans, Cards, Wakala
84 |  | Build accordion components
84 |  | Write General FAQs
84 |  | Write Account FAQs
84 |  | Write Digital Banking FAQs
84 |  | Write Loans FAQs
84 |  | Write Cards FAQs
84 |  | Write Wakala FAQs
84 |  | Add search/filter functionality
84 |  | Add CTA to Contact Us
84 |  | SEO: FAQ schema markup (JSON-LD)
84 |  | Mobile responsive accordion
85 | Build: Blog / News Page | Design blog listing with featured hero
85 |  | Build blog card grid
85 |  | Build individual post template
85 |  | Add category filter
85 |  | Add pagination
85 |  | Add social sharing buttons
85 |  | Add related posts section
85 |  | Create 3-5 sample posts
85 |  | Add blog SEO metadata
85 |  | Mobile responsive layout
86 | Build: Privacy & Terms | Request approved Privacy Policy from CBT legal
86 |  | Request approved Terms of Service from CBT legal
86 |  | Build Privacy Policy page with TOC
86 |  | Build Terms page with TOC
86 |  | Add last updated date
86 |  | Add print-friendly styling
86 |  | Link from footer, cookie banner, forms
86 |  | Mobile readable typography
87 | Build: Cookie Consent | Build banner component (bottom viewport)
87 |  | Add Accept/Reject/Customize buttons
87 |  | Build preferences modal (Essential, Analytics, Marketing)
87 |  | Implement localStorage persistence
87 |  | Conditionally load GA4 based on consent
87 |  | Link to Privacy Policy
87 |  | Style to match brand (blue-green gradient)
87 |  | Test on mobile (must not block content)
87 |  | Show on first visit, hide after choice
112 | Awaiting: Product Master List | Request official list from CBT marketing
112 |  | Confirm Personal Banking Savings names
112 |  | Confirm Fixed Accounts names
112 |  | Confirm Group Accounts names
112 |  | Verify USD/EUR/GBP: real products or display?
112 |  | Update all product pages
112 |  | Update mega menu with final categories
113 | Awaiting: Email Domain | Ask CBT: @coopbank.co.tz or @cbtbank.co.tz?
113 |  | Receive written confirmation
113 |  | Update Homepage footer email
113 |  | Update Contact Us page email
113 |  | Update all mailto: links
113 |  | Update careers email
113 |  | Update whistleblower email
113 |  | Full grep and replace all refs
115 | Awaiting: About Us Content | Request Our Story / History
115 |  | Request Mission Statement
115 |  | Request Vision Statement
115 |  | Request Core Values + descriptions
115 |  | Request board photos & bios
115 |  | Request management photos & bios
115 |  | Build Our Story timeline
115 |  | Build Mission & Vision cards
115 |  | Build Core Values grid
115 |  | Update photo gallery
115 |  | Final proofread
116 | Awaiting: Account Opening CTAs | Ask: external portal URL?
116 |  | Ask: downloadable PDF?
116 |  | Ask: email/phone process?
116 |  | Receive confirmed destination
116 |  | Update Homepage hero CTA
116 |  | Update Personal Banking CTAs
116 |  | Update Fixed Deposit CTA
116 |  | Update Group Accounts CTA
116 |  | Update Digital Banking CTA
116 |  | Update mobile app links
116 |  | Test all CTAs desktop + mobile
116 |  | Verify no broken links
118 | Awaiting: Agent Database | Request from CBT ops (CSV/Excel)
118 |  | Define format: Name ¦ Location ¦ Region ¦ Contact ¦ GPS
118 |  | Receive and validate data
118 |  | Clean and normalize data
118 |  | Create agents JSON/API endpoint
118 |  | Build agent locator search UI
118 |  | Build agent card component
118 |  | Integrate Google Maps pins
118 |  | Add geolocation: Find Nearest Agent
118 |  | Add region filter dropdown
118 |  | Mobile responsive locator
118 |  | Test with sample data
118 |  | Populate production data
66 | Swahili Translation | Set up i18n framework
66 |  | Translate Homepage
66 |  | Translate Personal Banking
66 |  | Translate Digital Banking
66 |  | Translate Loan Products
66 |  | Translate About Us
66 |  | Translate Business Banking
66 |  | Translate Contact/FAQs/Blog
66 |  | Translate Careers/Tenders/Whistleblower
66 |  | Translate Privacy/Terms
66 |  | Build EN/SW toggle in navbar
66 |  | Persist language in localStorage
66 |  | Test Swahili layouts
66 |  | Native speaker review
66 |  | QA all Swahili pages
70 | Cross-Browser Testing | Chrome desktop + mobile
70 |  | Safari desktop + iOS
70 |  | Firefox desktop
70 |  | Edge desktop
70 |  | Samsung Internet Android
70 |  | Breakpoints: 320, 375, 414, 768, 1024, 1440
70 |  | Landscape orientation
70 |  | Fix overflow issues
70 |  | Test interactive elements
70 |  | Test mega menu
70 |  | Test chatbot mobile
70 |  | Test forex ticker
74 | DNS Migration & Go-Live | Get DNS credentials from CBT IT
74 |  | Backup current coopbank.co.tz
74 |  | Configure production Cloud Run
74 |  | Set up domain + SSL
74 |  | Update DNS records
74 |  | Configure 301 redirects
74 |  | Verify DNS propagation
74 |  | E2E test production
74 |  | Submit sitemap to Search Console
74 |  | Verify GA4 on production
74 |  | Monitor first 24 hours
76 | Post-Launch Monitoring | Set up uptime monitoring
76 |  | Configure error alerting
76 |  | Week 1: Daily performance check
76 |  | Week 1: Search Console monitoring
76 |  | Week 2: Review GA4 analytics
76 |  | Week 2: Fix reported issues
76 |  | Week 3-4: Weekly review
76 |  | Week 3-4: Remaining bugs
76 |  | Day 30: Final performance report
76 |  | Day 30: Credential handover
76 |  | Day 30: Discuss maintenance contract

## Gantt
Project Timeline (Gantt) | [31 empty] | April | [29 empty] | May
Task | Status | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
DISCOVERY & PLANNING
Discovery & Requirements | Complete
Competitor Analysis | Complete
Sitemap & IA | Complete
Content Audit | Complete
DESIGN & BUILD
Project Setup | Complete
Homepage Build | Complete
Personal/Loan Pages | Complete
Digital Banking Pages | Complete
About/Careers/Tenders | Complete
Navbar, Footer, Components | Complete
Chatbot + GA4 | Complete
CLIENT REVIEW & REVISIONS
First Draft Submitted | Complete
Feedback Round 1 | Complete
Revisions Round 1 | Complete
Business Banking Page | Not Started
Contact Us + FAQs | Not Started
Blog + Privacy/Terms + Cookie | Not Started
Figma Design System | Not Started
AWAITING CLIENT (13 items) | Blocked
Feedback Round 2 | Not Started
Feedback Round 3 (Final) | Not Started
CONTENT & LOCALIZATION
Swahili Translation | Not Started
Branch Directory + Maps | Not Started
API Integrations | Not Started
Final Content & Media | Not Started
TESTING & QA
Cross-Browser Testing | Not Started
SEO & Performance | Not Started
Security & BOT Compliance | Not Started
UAT with CoopBank | Not Started
GO-LIVE & HANDOVER
DNS Migration & Launch | Not Started
Staff Training | Not Started
Post-Launch Monitoring (30d) | Not Started

## Activity Log
Activity Log — Track status changes here
Date | Task ID | Task Name | Field | Old Value | New Value | Changed By
2026-03-26 | - | Project Tracker Created | Setup | - | All tasks imported from CRM | System

## Stakeholders
Project Stakeholders
Name | Email | Role | Organization | Key Responsibility
Jumbe Seleman | jumbenylon@gmail.com | Lead Developer | Saccura Group | Full-stack dev, architecture, deployment
Mwana Neema Semboja | neema.semboja@sakuragroup.co.tz | Project Manager | Saccura Group | Client liaison, content, PM
Oscar Rubasha | Oscar.Ruhasha@cbtbank.co.tz | Main Feedback Contact | CBT Bank | Primary reviewer — all feedback through Oscar
Moses Mpakasi | Moses.Mpakasi@cbtbank.co.tz | Key Stakeholder | CBT Bank
Yahya Kinabo | Yahya.Kiyabo@cbtbank.co.tz | Key Stakeholder | CBT Bank
Martin Malopa | Martin.Malopa@cbtbank.co.tz | Key Stakeholder | CBT Bank
Geoffrey Nangai | Geoffrey.Nangai@cbtbank.co.tz | Key Stakeholder | CBT Bank
Tecla Muchunguzi | Tecla.Muchunguzi@cbtbank.co.tz | Key Stakeholder | CBT Bank
Samson Msangi | Samson.Msangi@cbtbank.co.tz | Key Stakeholder | CBT Bank
Hemed Nassor | Hemed.Nassor@cbtbank.co.tz | Primary Contact | CBT Bank
Robin Makwabe | Robin.Makwabe@cbtbank.co.tz | Stakeholder (CC) | CBT Bank